Mission Plan & Itinerary:

Mission #IOS-9737 - CSS TULLY 20 October - 2 November 1997

Area of Operation: Haro-Juan de Fuca Straits, west coast Vancouver Island, southern Queen Charlotte Sound, Strait of Georgia, Jervis Inlet, Inner Line P

Summary of Objectives: Plankton and water sampling, and acoustic zooplankton sampling in support of La Perouse and GLOBEC programs, and the 1997-98 El Nino Watch .

Specific objectives:

1) CTD/rosette and plankton tows along station line out Haro Strait to measure nutrient

input to Georgia Basin

2) CTD/rosette and plankton tows along standard La Perouse Project survey lines, Juan de Fuca to Brooks Peninsula

3) CTD sampling along inner Line P stations to monitor possible El Nino effects along the west coast

4) Participate in MARCOT program with Canadian Navy

5) Daylight acoustic surveys of euphausiid scattering layer density in the Strait of Georgia and Jervis Inlet

Chief Scientist: 	D. Yelland (363-6321)

Scientific personnel:

|  | D. Moore (IOS) |
| --- | --- |
|  | S. Romaine (IOS) |
|  | B. Bornhold (UBC) |
|  | J. Putland (IOS) |
|  | B. Minkley (IOS) |
|  | M. Robert (IOS) |
|  | H. MacLean (UBC) |
|  | S. Harris (UBC) |
|  | D. Varela (UBC) |
|  | M. Bentley (CWS) |
|  | M. Force (CWS) |
|  | D. Mackas (IOS) (week 2 only) |
|  | B. Wai (Prov. BC)(week 2 only) |

Ship’s equipment required:

GPS positioning

seawater sampling loop

Depth sounder

Radar

(SAIL)

ADCP

Deck machinery required:  (see deck plan to follow)

A-frame centerline aft, with heave compensator

crane

capstan

329 #1233 “BIONESS” winch

329 #1482 CTD winch, 3800 m 0.316” cable

420 #1432 hydro winch, 2000+ m of hydro wire, mounted near chains

Other equipment to be loaded:

Laboratory instruments and computers

BIONESS

CTD/rosettes (2)

misc. plankton sampling gear (nets and acoustics)

chest freezer

Anticipated loading time: 1 day

Provisional schedule:

20 October: Load and test scientific gear

20 October: Depart IOS 1800. Haro-Juan de Fuca station line, then continue out Juan de Fuca Strait to La Perouse survey area.

21-27 October: La Perouse CTD and plankton lines LA-LBP (lines LC, LG, LBP plus off-line plankton stations C1-C3 and B7-B8 are highest priority). Inner Line P CTD stations to be sampled to 1000m only. Approximately 70 CTD stations of which approx 35 with rosette casts.

27 October: Pick up D. Mackas and B. Wai, drop off UBC personnel.  Time and location of exchange to be determined.

27-2 November: COPRA station lines off north end of Vancouver Island; acoustic survey, Strait of Georgia; acoustic survey, Jervis Inlet/Malaspina St.

Station list:

Haro-Juan de Fuca stations:

Saanich	48 39.4		123 30.0		170 m		CTD/R

Sat. Ch.	48 43.4		123 25.8		85 m		CTD/R

Swanson	48 44.3		123 17.4		160 m		CTD/R

Stuart I		48 40.9		123 15.3		336 m		CTD/R, 2 bongos

Haro		48 33.8		123 13.3		290 m		CTD/R

SH11		48 28.7		123 08.6		280 m		CTD/R

Hein Is.	48 22.8		123 02.6		153 m		CTD/R, 2 bongos

Sill		48 15.7		123 10.0		128 m		CTD/R

JDF		48 16.0		123 25.0		154 m		CTD/R, 2 bongos

La Perouse standard grid:

_____________________________________________________________________

-Plankton Stations:

A1 (=LC8)	48 29.45		126 07.1		200

A2		48 22.7		126 03.8		400

A3 (~LC9)	48 24.7		126 15.8		900

A4 (=LC12)	48 15.0		126 40.0		>1000

B3		48 51.08		125 39.2		45

B5 (~LC5)	48 40.6		125 46.25		90

B6 (=LC6)	 48 36.46		125 54.0		95

B7 (=LCB4)	48 32.0		125 35.5		76

B8 (=LCB3)	48 34.5		125 30.0		120

C1		48 28.93		125 15.3		150	CTD/R	NOTE: this station 											must be occupied in 	the 											morning daylight hours

C2 (=LBA2)	48 25.4		125 07.8		115

C3 (=LBA3)	48 23.45		125 20.8		120

E1 (=LBA1)	48 31.7		125 03.8		100

D1 (=LD2) 	48 58.35		125 47.05		42

D2 (=LD4) 	48 53.16		125 57.0		60

__________________________________________________________

-CTD/Rosette Stations: (NOTE: not all listed stations are to be occupied)

A-LINE

LA1		48 29.23		124 43.65		260	CTD/DO2

LA2		48 26.25		124 51.32		305	CTD/DO2

LA3		48 22.84		124 57.72		100	CTD

LA4		48 19.36		125 04.12		175	CTD/DO2

LA5		48 16.08		125 10.60		118	CTD

LA6		48 12.63		125 17.2		110	CTD/DO2

LA7		48 09.20		125 23.86		115	CTD

LA8		48 05.78		125 30.40		138	CTD/DO2

LA9		48 02.36		125 36.92		310	CTD

LA10		47 59.02		125 43.40		900	CTD

_________________________________________________________

B-LINE

LB1		48 40.40		124 59.48		30	CTD/DO2

LB2	(m)	48 39.00		125 02.40		55	CTD/DO2

LB3		48 37.32		125 05.58		92	CTD

LB4		48 35.67		125 08.72		105	CTD/DO2

LB5		48 34.00		125 12.00		95	CTD

LB6		48 32.18		125 15.51		110	CTD/DO2

LB7		48 28.68		125 22.10		152	CTD

LB8	(m)	48 25.30		125 28.65		145	CTD/DO2

LB9	(m)	48 22.0		125 34.8		135	CTD/DO2

LB10	(m)	48 18.57		125 41.35		150	CTD

LB11		48 15.2		125 47.75		200	CTD/DO2

LB12		48 12.92		125 51.9		510	CTD/DO2

LB13		48 10.6		125 56.12		810	CTD

LB14		48 08.48		126 00.0		1180	CTD/DO2

LB15		48 04.36		126 08.46		1450	CTD

LB16		48 00.53		126 17.00		1530	CTD	NOTE: this station 											must be occupied in

the morning 												daylight hours

C-LINE

LC1		48 50.44		125 27.73		90	CTD/DO2

LC2	(m)	48 48.68		125 30.95		105	CTD/DO2

LC3		48 46.95		125 34.24		130	CTD

LC4		48 43.43		125 40.8		162	CTD/DO2	NOTE: this station 											must be occupied in the 											morning daylight hours

LC5		48 39.94		125 47.4		90	CTD

LC6		48 36.46		125 54.0		95	CTD

LC7	(m)	48 32.96		126 00.5		125	CTD/DO2

LC8	(m)	48 29.45		126 07.1		197	CTD/DO2	NOTE: this station 											must be occupied in the 											morning daylight hours

LC9		48 25.94		126 13.7		660	CTD/DO2	NOTE: this station 											must be occupied in the 											morning daylight hours

LC10	(m)	48 22.4		126 20.2		1150	CTD

LC11	(m)	48 18.95		126 26.7		1470	CTD/DO2

LC12		48 15.0		126 40.0		?	CTD

__________________________________________________________

D-LINE

LD1		49 00.1		125 43.8		33	CTD/DO2

LD2	(m)	48 58.35		125 47.05		42	CTD/DO2

LD3		48 56.61		125 50.4		43	CTD

LD4	(m)	48 53.16		125 57.0		60	CTD/DO2

LD5		48 49.65		126 03.6		85	CTD

LD6		48 46.18		126 10.2		135	CTD/DO2

LD7	(m)	48 42.67		126 16.8		475	CTD

LD8		48 39.17		126 23.4		760	CTD/DO2

LD9	(m)	48 35.69		126 30.0		1095	CTD

LD10		48 32.2		126 36.6		1475	CTD/DO2

LD11		48 28.76		126 42.94		1560	CTD

__________________________________________________________

E-LINE

LE1		49 07.0		126 00.9		47	CTD/DO2

LE2		49 04.3		126 04.5		55	CTD/DO2

LE3		49 00.5		126 10.6		79	CTD

LE4		48 56.5		126 15.1		117	CTD/DO2

LE5		48 52.8		126 20.4		155	CTD

LE6		48 48.5		126 26.3		197	CTD/DO2

LE7		48 44.2		126 32.1		463	CTD

LE8		48 40.3		126 38.0		?	CTD/DO2

LE9		48 36.0		126 44.0		?	CTD

_________________________________________________________

F-LINE

LF1		49 14.8		126 14.3		37	CTD/DO2

LF2		49 13.2		126 16.5		56	CTD/DO2

LF3		49 09.6		126 21.9		89	CTD

LF4		49 05.9		126 27.5		126	CTD/DO2

LF5		49 02.0		126 33.2		151	CTD

LF6		48 58.1		126 38.9		458	CTD/DO2

LF7		48 54.1		126 44.8		718	CTD

LF8		48 50.0		126 50.7		1003	CTD/DO2

LF9		48 45.8		126 56.8		1117	CTD

_________________________________________________________

G-LINE (ESTEVAN POINT)

LG1	(m)	49 20.5		126 35.0		55	CTD/DO2

LG2		49 18.7		126 38.1		105	CTD/DO2

LG3		49 15.0		126 43.7		112	CTD	NOTE: this station 											must be occupied in the 											morning daylight hours

LG4	(m)	49 11.3		126 49.4		146	CTD/DO2

LG5		49 07.4		126 55.3		258	CTD	NOTE: this station 											must be occupied in the 											morning daylight hours

LG6		49 03.5		127 01.2		866	CTD/DO2	NOTE: this station 											must be occupied in the 											morning daylight hours

LG7	(m)	48 59.4		127 07.2		1061	CTD

__________________________________________________________

H-LINE

LH1		49 34.3		126 44.2		35	CTD/DO2

LH2		49 32.2		126 47.4		49	CTD/DO2

LH3		49 28.7		126 52.9		97	CTD

LH4		49 24.9		126 58.7		126	CTD/DO2

LH5		49 21.3		127 04.5		156	CTD

LH6		49 17.6		127 10.4		354	CTD/DO2

LH7		49 13.7		127 16.4		>1000	CTD

LH8		49 09.7		127 22.5		>1000	CTD/DO2

LH9		49 05.6		127 28.7		>1000	CTD

___________________________________________________________

J-LINE

LJ1		49 44.3		127 02.5		63	CTD/DO2

LJ2		49 42.6		127 05.3		79	CTD/DO2

LJ3		49 39.1		127 11.1		128	CTD

LJ4		49 35.5		127 16.9		154	CTD/DO2

LJ5		49 31.66		127 22.56		?	CTD

LJ6		49 27.9		127 28.58		?	CTD/DO2

LJ7		49 24.05		127 34.72		?	CTD

LJ8		49 20.11		127 40.96		?	CTD/DO2

LJ9		49 16.07		127 47.33		?	CTD

K-LINE (SLIGHTLY NW OF SK LINE)

LK1		49 55.5		127 18.7		37	CTD

LK2		49 53.9		127 21.7		70	CTD

LK3		49 50.5		127 27.6		76	CTD

LK4		49 46.9		127 33.6		134	CTD

LK5		49 43.3		127 39.6		805	CTD

LK6		49 39.5		127 45.8		767	CTD

LK7		49 35.7		127 52.1		1064	CTD

LK8		49 31.5		127 58.5		>1000	CTD

__________________________________________________________

L-LINE

LL1		50 02.2		127 39.3		72

LL2		49 59.34		127 44.03		134

LL3		49 55.75		127 50.18		585

LL4		49 52.08		127 56.43		872

LL5		49 48.33		128 02.81		1765

LL6		49 44.49		128 09.3		?

LL7		49 40.57		128 15.92		?

LL8		49 36.55		128 22.68		?

BP-LINE (BROOKS PENINSULA)

LBP1	(m)	50 04.8		127 52.8		32

LBP2		50 04.0		127 54.2		105		NOTE: this station 											must be occupied in

the morning 												daylight hours

LBP3	(m)	50 03.2		127 55.3		172

LBP4		50 01.4		127 58.1		1106		NOTE: this station 											must be occupied in

the morning 												daylight hours

LBP5	(m)	50 00.0		128 00.0		1230

LBP6	(m)	49 56.2		128 05.5		?

LBP7		49 52.4		128 11.2		?		NOTE: this station 											must be occupied in

the morning 												daylight hours

LBP8		49 48.6		128 16.8		?

M-LINE

LM1		50 12.6		127 57.49		?

LM1A		50 10.95		128 00.66		85

LM2		50 09.03		128 03.78		155

LM3		50 05.39		128 10.2		1180

LM4		50 01.68		128 16.73		?

LM5		49 57.88		128 23.39		?

LM6		49 54.00		128 30.17		?

___________________________________________________________

Line P Stations (CTD only)__

P01		48 34.5		125 30.0

P02		48 36.0		126 00.0

P03		48 37.5		126 20.0

P04		48 39.0		126 40.0

P05		48 41.6		127 10.0

P06		48 44.6		127 40.0

P07		48 46.6		128 10.0

P08		48 49.0		128 40.0

P09		48 51.4		129 10.0

P10		48 53.6		129 40.0

P11		48 56.0		130 10.0

P12		48 58.2		130 40.0

_________________________________________________

Cape Scott COPRA lines: (CTD/R + bongos)

LQ03		50 39.8		129 01.9		750

JI22		50 39.8		129 17.6

CPE2		50 43.0		128 40.0		140

CS3B		51 00.0		129 27.0

CS2B		50 56.0		129 00.0

CS1B		50 53.0		128 40.0

CPE1		51 00.0		127 50.0		150

____________________________________________________________________

St. of Georgia station: (CTD/R)

GEO1 		49 15.00		123 44.9		400

Strait of Georgia acoustics survey waypoints:

Cape Mudge to:

| Waypoint | Lat | Long | Landmark | Time/Date | Comments |
| --- | --- | --- | --- | --- | --- |
| 1 | 49 49.5 | 124 36.3 |  |  |  |
| 2 | 49 48.4 | 124 32.0 | Grief Pt |  |  |
| 3 | 49 45.7 | 124 32.0 |  |  |  |
| 4 | 49 45.7 | 124 24.3 | Albion Pt. |  |  |
| 5 | 49 42.7 | 124 21.1 | Northeast Pt |  |  |
| 6 | 49 42.7 | 124 14.2 |  |  |  |
| 7 | 49 38.4 | 124 16.5 |  |  |  |
| 8 | 49 36.5 | 124 05.4 |  |  |  |
| 9 | 49 21.6 | 124 07.3 |  |  |  |

Jervis Inlet:

| Upper Jervis: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| J1 | 50o05.5' | 123o47.5 | Patrick Pt. |  |  |
| J2 | 50o02.3' | 123o50.0 |  |  |  |
| J3 | 50o01.6' | 123o55.5 |  |  |  |
| J4 | 49o58.5' | 124o00.0 |  |  |  |
| J5=B12 | 49o53.65' | 123o55.0 |  |  |  |
| (S=17.5 miles) |  |  |  |  |  |

| Hotham: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| H1=A8 | 49o48.0' | 124o04.5 | Culloden Pt. |  |  |
| H2 | 49o49.1' | 124o00.4 |  |  |  |
| H3 | 49o50.15' | 124o02.1 | Elephant Pt. |  |  |
| H4 | 49o51.2' | 124o00.3 | waterfall |  |  |
| H5 | 49o52.5' | 124o03.65 |  |  |  |
| H6 | 49o53.6' | 124o02.6 |  |  |  |
| H7 | 49o50.0' | 124o01.4 | BIONESS track |  |  |
| H8 | 49o48.0' | 124o02.0 | BIONESS track |  |  |
| (S=16 miles) |  |  |  |  |  |

| Detail A |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| A1 | 49o55.0' | 123o53.25 | Vancouver Bay |  |  |
| A2 | 49o52.7' | 123o54.0 | Saumarez Bluff |  |  |
| A3 | 49o50.55' | 123o52.7 | gravel pit |  |  |
| A4 | 49o49.7' | 123o55.0 | Dacres Pt. |  |  |
| A5 | 49o48.1' | 123o55.0 |  |  |  |
| A6 | 49o48.25' | 123o58.0 | Foley Hd. |  |  |
| A7 | 49o47.1' | 124o01.2 |  |  |  |
| A8 | 49o48.0' | 124o04.5 | Culloden Pt. |  |  |
| A9 | 49o46.3' | 124o05.75 |  |  |  |
| A10 | 49o46.75' | 124o08.5 | Ahlstrom Pt. (hydro) |  |  |
| A11 | 49o45.2' | 124o11.5 |  |  |  |
| A12 | 49o46.2' | 124o15.8 | Thunder Bay |  |  |
| A13 | 49o43.9' | 124o13.7 | Alexander Pt. |  |  |
| (S=27 miles) |  |  |  |  |  |

| Detail B |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| B1 | 49o45.0' | 124o15.3 | Evenden Pt. |  |  |
| B2 | 49o46.5' | 124o12.3 |  |  |  |
| B3 | 49o45.7' | 124o08.2 | (hydro line) |  |  |
| B4 | 49o47.45' | 124o06.7 |  |  |  |
| B5 | 49o46.75' | 124o03.3 |  |  |  |
| B6 | 49o49.7' | 124o02.9 | Junction Is. |  |  |
| B7 | 49o46.7' | 123o56.9 | Egmont Pt. |  |  |
| B8 | 49o48.85' | 123o56.9 | Sydney Is. |  |  |
| B9 | 49o48.85' | 123o53.8 |  |  |  |
| B10 | 49o51.25' | 123o54.7 |  |  |  |
| B11 | 49o52.7' | 123o52.1 | Perketts Cr. |  |  |
| B12 | 49o53.65' | 123o55.0 |  |  |  |
| B13 | 49o55.0' | 123o52.8 | Vancouver Bay |  |  |
| (S=30 miles) |  |  |  |  |  |