EXPEDITION PLAN AND ITINERARY

DEPARTMENT:  DFO, Ocean Sciences and Productivity Division

MISSION NO:  2003-01

MISSION AREA: Line P, Station Papa, North-East Pacific

MISSION OBJECTIVE: Repeat hydrography section, deploy Argo floats.

SHIP:  John P. Tully

DATE, FROM:  Feb 3 	TO:  Feb 22, 2002

SENIOR SCIENTIST:  Marie Robert

SCIENTIFIC PERSONNEL:  8 berths required

| Female | Male |
| --- | --- |
| Marie Robert | ## Doug Anderson |
| Nes Sutherland | Ron Perkin |
| Sheila Toews | Darren Tuele |
|  | James Zwiers |
|  | Mike Bentley |

SHIP EQUIPMENT REQUIRED: depth sounder, sea water supply to lab, heave compensator, tugger winch, Zodiac

DECK MACHINERY REQUIRED:

Note: The details are on the deck plan, to follow.

OTHER EQUIPMENT TO BE LOADED:  Scientific gear (lab instruments, sampling equipment, etc.)

ANTICIPATED LOADING TIME:  1 day for scientific gear.

DANGEROUS CHEMICALS:

[INCLUDING MATERIAL SAFETY DATA SHEETS AND WHMIS LABELS]

Oxalic Acid – Hydrochloric Acid – Ammonium Hydroxide – H3PO4 – H2SO4 – Sodium Hydroxide – Acetone –Isopropyl Alcohol – Formalin –Ethyl Alcohol – Polyform – 14C Bicarbonate – 3 tanks of compressed air - NOTE: This list needs to be updated.

Station List:

| Station | Latitude deg min N | Longitude deg min W | Bottom Depth m | St'n Time h | Sampling |
| --- | --- | --- | --- | --- | --- |
| Saanich Inlet |  |  |  |  |  |
| S3 | 48 35.6 | 123 30.0 | 225 | 3 | Rosette |
| Juan de Fuca Surface Samples |  |  |  |  |  |
| JF1 | 48 16.0 | 123 30.0 | 150 | 0 | underway |
| JF2 | 48 18.0 | 124 00.0 | 180 | 0 | underway |
| JF3 | 48 27.0 | 124 30.0 | 230 | 0 | underway |
| JF4 | 48 32.3 | 125 00.0 | 60 | 0 | underway |
| Line P CTD and water sampling survey |  |  |  |  |  |
| P1 | 48 34.5 | 125 30.0 | 120 | 0.5 | CTD, B-10 |
| P2 | 48 36.0 | 126 00.0 | 114 | 1 | CTD, B-10 |
| P3 | 48 37.5 | 126 20.0 | 730 | 1 | CTD, B-10 |
| P4 | 48 39.0 | 126 40.0 | 1300 | 6 | Rosette, Bongo |
| P5 | 48 41.5 | 127 10.0 | 2100 | 1.5 | CTD, 1500 m |
| P6 | 48 44.6 | 127 40.0 | 2500 | 4 | CTD, 1500 m |
| P7 | 48 46.6 | 128 10.0 | 2450 | 1.5 | CTD, 1500 m |
| P8 | 48 49.0 | 128 40.0 | 2440 | 8 | Rosette (1500m), Bongo |
| P9 | 48 51.4 | 129 10.0 | 2340 | 1.5 | CTD, 1500 m |
| P10 | 48 53.6 | 129 40.0 | 2660 | 1.5 | CTD, 1500 m |
| P11 | 48 56.0 | 130 10.0 | 2700 | 1.5 | CTD, 1500 m |
| P12 | 48 58.2 | 130 40.0 | 3300 | 8 | Rosette, Bongo |
| P13 | 49 02.6 | 131 40.0 | 2875 | 1.5 | CTD, 1500 m |
| P14 | 49 07.4 | 132 40.0 | 3275 | 1.5 | CTD, 1500 m |
| P15 | 49 12.0 | 133 40.0 | 3200 | 1.5 | CTD, 1500 m |
| P16 | 49 17.0 | 134 40.0 | 3550 | 8 | Rosette, Bongo |
| P17 | 49 21.0 | 135 40.0 | 3200 | 1.5 | CTD, 1500 m |
| P18 | 49 26.0 | 136 40.0 | 3775 | 1.5 | CTD, 1500 m |
| P19 | 49 30.0 | 137 40.0 | 3850 | 1.5 | CTD, 1500 m |
| P20 | 49 34.0 | 138 40.0 | 3890 | 8 | Rosette, Bongo |
| P21 | 49 38.0 | 139 40.0 | 3840 | 1.5 | CTD, 1500 m |
| P22 | 49 42.0 | 140 40.0 | 3880 | 1.5 | CTD, 1500 m |
| P23 | 49 46.0 | 141 40.0 | 3970 | 1.5 | CTD, 1500 m |
| P24 | 49 50.2 | 142 40.0 | 3910 | 1.5 | CTD, 1500 m |
| P25 | 50 00.0 | 143 36.3 | 3890 | 1.5 | CTD, 1500 m |
| P35 | 50 00.0 | 144 18.2 | 4170 | 1.5 | CTD, 1500 m |
| P26 | 50 00.0 | 145 00.0 | 4250 | 10 | Rosette, Bongo, Carbonates,Drifter |
| Argo 1 | 43 00.0 | 138 00.0 | ? | 2 | Ros 2000m, Bongo, Argo |
| Argo 2 | 42 30.0 | 135 00.0 | ? | 2 | Ros 2000m, Bongo, Argo |
| Argo 3 | 42 00.0 | 132 00.0 | ? | 2 | Ros 2000m, Bongo, Argo |
| Argo 4 | 41 30.0 | 129 00.0 | ? | 2 | Ros 2000m, Bongo, Argo |
| Argo 5 | 41 00.0 | 126 00.0 | ? | 2 | Ros 2000m, Bongo, Argo |

Note: Stations Argo 1 to 5 will be on a line between 40°N and 43°N, not decided  at which latitude yet.

Itinerary

Feb 3	  	Load at IOS.

Feb 4, 1300.  	Depart for a test station in Saanich Inlet, then proceed towards Line P.

(Depart as soon as the Rosette/CTD gear is ready and working)

Feb 5 	  	Sample Line P stations en route to Stn Papa.

Feb 13		Depart Station Papa

Feb 16		Start Argo Line

Feb 21	Back to Pat Bay and offload (most of the gear stays on board for Peña's cruise, 2003-02, leaving Feb 24).

### Cruise track