PACIFIC REGION CCG VESSEL CRUISE PLAN

DEPARTMENTS:   Fisheries and Oceans, Canada

SCIENCE CRUISE NUMBER:	IOS2003-15

NAME OF SHIP/PLATFORM:  John P Tully

SURVEY AREA/AREA OF OPERATION: West coast of Vancouver Island, Juan de Fuca Strait to southern Queen Charlotte Sound

CRUISE OBJECTIVE[S]:

- Biological oceanography time series, west coast Vancouver Island

- Nestucca Project sampling of oceanographic conditions affecting the Triangle Island seabird colony

- Biological and acoustic sampling in Knight Inlet

DATE:		FROM:	 16 May 2003			TO:  26 May 2003

SENIOR SCIENTIST[S]/CONTACT TEL. #’S:

Doug Yelland, tel 363-6321, e-mail:  yellandd@pac.dfo-mpo.gc.ca

SCIENTIFIC PERSONNEL:		BERTHS REQUIRED: 12

| MALE [NAMES] | FEMALE[NAMES] |
| --- | --- |
| Doug Yelland | Sheila Teows |
| Doug Moore | Maia Tsurumi |
| Lucius Perrault | Tanja Gschwind |
| Peter Sutherland | Rana El-Sabaawi |
|  | Rachelle Provencal |

SHIP EQUIPMENT REQUIRED:

12 KHz sounder

heave compensator and A-frame

aft deck crane for loading/unloading and moorings

capstan

seawater sampling pump(s)

DECK MACHINERY REQUIRED:  [DECK PLAN TO FOLLOW; in common with Juhasz/Thomson cruise immediately preceeding]

CTD winch, aft deck

BIONESS winch, aft deck

Mooring winch aft deck

Hydro winch (starboard chains)

Hydro or work winch, aft deck, with at least 500m of hydro wire (or heavier) for bongo net tows from stern

OTHER EQUIPMENT TO BE LOADED:

scientific equipment into lab, chart room

SPECIAL REQUIREMENTS:  [INCLUDE LAUNCH/SMALL BOAT REQUIREMENTS AND  SPECIAL POWER REQUIREMENTS]

- seawater supply to lab at a minimum flow rate of 20 L per min

- possible use of 733 or launch for scientific crew exchange, dependant on location

DANGEROUS CHEMICALS:  [INCLUDING MSDS AND WHMIS LABELS]

GAS CYLINDERS: none

ACIDS & BASES	hydrochloric acid, 20 L

sulphuric acid, 0.5 L

ammonium hydroxide, 2 L

TOXIC:	Formaldehyde, 20 L

Glutaraldehyde, 1 L

Oxalic acid, 100 g

Phenol, 200 g

Lugol's iodine 0.5L

Ammonium formate 2L

FLAMMABLES:acetone, 20L

ethanol 15L

isopropanol 2L

RADIOISOTOPES

ANTICIPATED LOADING TIME:

1 day, 15 September 2002

LOGISTICS:

COMMENCE LOADING [DATE/TIME]: 15-16 May 2003

SAILING [DATE/TIME]: evening of 16 May

EXPECTED OPERATIONS  PROFILE: 24 h per day

[24 HR./12 HR/OTHER]

RETURNING [DATE/TIME]: May 26 morning (possible small scientific crew exchange at Pt. McNeill on or about May23)

OFFLOADING: [DATE/TIME]: IOS: 26 May, 2003

DATE		GENERAL AREA OF OPERATIONS

[LINES/MOORINGS/STATIONS]

16 May- transit IOS to southwest coast Vancouver Island

17 May– Begin CTD/Rosette/Bongo stations stations off Barkley Sound (1d), Esperanza Inlet or Estevan Point (1d), Brooks Peninsula (1d)

20 May- transit to CS line

21-22 May- CTD/Rosette/Bongo stations along CS line and outlying stations

22-23 May- Transit to Knight Inlet (possible stop in Port McNeill to pick up additional scientific party

23-24 May- Acoustic and net tow operations in Knight Inlet

25 May-transit to Pat Bay

26 May (AM)- off load

PROPOSED CRUISE

ITINERARY:

N.B.: ALSO ATTACH LIST OF

STATIONS, MOORING

OPERATIONS, OR SURVEY

LINES IDENTIFYING EXACT

POSITIONS.

Station List

Southern Vancouver Island PLANKTON STATIONS:

A1 (=LC8)	48 29.45		126 07.1		200

A2		48 22.7		126 03.8		400

A3 (~LC9)	48 24.7		126 15.8		900

A4 (=LC12)	48 15.0		126 40.0		>1000

B3		48 51.08		125 39.2		45

B5 (~LC5)	48 40.6		125 46.25		90

B6 (=LC6)	 48 36.46		125 54.0		95

B7 (=LCB4)	48 32.0		125 35.5		76

B8 (=LCB3)	48 34.5		125 30.0		120

C1		48 28.93		125 15.3		150

C2 (=LBA2)	48 25.4		125 07.8		115

C3 (=LBA3)	48 23.45		125 20.8		120

E1 (=LBA1)	48 31.7		125 03.8		100

____________________________________________________________________________________

B-LINE

LB1		48 40.40		124 59.48		30		CTD/DO2

LB2		48 39.00		125 02.40		55		CTD/DO2

LB3		48 37.32		125 05.58		92		CTD

LB4		48 35.67		125 08.72		105		CTD/DO2

LB5		48 34.00		125 12.00		95		CTD

LB6		48 32.18		125 15.51		110		CTD/DO2

LB7		48 28.68		125 22.10		152		CTD

LB8		48 25.30		125 28.65		145		CTD/DO2

LB9		48 22.0		125 34.8		135		CTD/DO2

LB10		48 18.57		125 41.35		150		CTD

LB11		48 15.2		125 47.75		200		CTD/DO2

LB12		48 12.92		125 51.9		510		CTD/DO2

LB13		48 10.6		125 56.12		810		CTD

LB14		48 08.48		126 00.0		1180		CTD/DO2

LB15		48 04.36		126 08.46		1450		CTD

LB16		48 00.53		126 17.00		1530		CTD

C-LINE

LC1		48 50.44		125 27.73		90		CTD/DO2

LC2		48 48.68		125 30.95		105		CTD/DO2

LC3		48 46.95		125 34.24		130		CTD

LC4		48 43.43		125 40.8		162		CTD/DO2

LC5		48 39.94		125 47.4		90		CTD

LC6		48 36.46		125 54.0		95		CTD

LC7		48 32.96		126 00.5		125		CTD/DO2

LC8		48 29.45		126 07.1		197		CTD/DO2

LC9		48 25.94		126 13.7		660		CTD/DO2

LC10		48 22.4		126 20.2		1150		CTD

LC11		48 18.95		126 26.7		1470		CTD/DO2

LC12		48 15.0		126 40.0		?		CTD

G-LINE (ESTEVAN POINT)

LG1		49 20.5		126 35.0	55	CTD/DO2

LG2		49 18.7		126 38.1	105	CTD/DO2

LG3		49 15.0		126 43.7	112	CTD

LG4		49 11.3		126 49.4	146	CTD/DO2

LG5		49 07.4		126 55.3	258	CTD

LG6		49 03.5		127 01.2	866	CTD/DO2

LG7		48 59.4		127 07.2	1061	CTD

## LG8		48 55.30		127 13.30	2070	CTD

LG9		48 51.2		127 19.4	~2100

J-LINE

LJ1		49 44.3		127 02.5		63		CTD/DO2

LJ2		49 42.6		127 05.3		79		CTD/DO2

LJ3		49 39.1		127 11.1		128		CTD

LJ4		49 35.5		127 16.9		154		CTD/DO2

LJ5		49 31.66		127 22.56		?		CTD

LJ6		49 27.9		127 28.58		?		CTD/DO2

LJ7		49 24.05		127 34.72		?		CTD

LJ8		49 20.11		127 40.96		?		CTD/DO2

LJ9		49 16.07		127 47.33		?		CTD

BP-LINE (BROOKS PENINSULA)

LBP1		50 04.8		127 52.8		32

LBP2		50 04.0		127 54.2    	105

LBP3		50 03.2		127 55.3		172

LBP4		50 01.4		127 58.1		1106

LBP5		50 00.0		128 00.0		1230

LBP6		49 56.2		128 05.5		?

LBP7		49 52.4		128 11.2		?

LBP8		49 48.6		128 16.8		?

Cape Scott/Triangle Island line:

CS1		50 34.9		129 41.5		>2000

CS2		50 41.3		129 28.0		approx 1800

CS3		50 45.6		129 20.0		200

CS4		50 49.2		129 13.0		100

CS5		50 56.0		129 00.0		64 (former COPRA CS2B)

CS6		51 00.0		128 50.0		65

CS7		51 04.5		128 44.0		65

CS8		51 08.5		128 36.0		138

CS9		51 12.5		128 28.0		195

CS10		51 16.5		128 20.0		78

____________________________________________________________________