Cruise Plan & Itinerary:

Cruise #IOS-2004-08 CCGS Vector   April 26 -  May 2, 2004

Area of Operation: Juan de Fuca Strait and Strait of Georgia

Summary of Objectives: CTD, bottle sampling, fluorometer, sediment grab samples.

Specific objectives:

- CTD/rosette along standard Juan de Fuca and Strait of Georgia lines (76 stations). The water from the rosette will be used for dissolved oxygen, nutrients and total organic carbon. In addition, a fluorometer will be used on rosette stations and a few bottom sediment grab samples will be collected.

Chief Scientist: 	Angelica Pena - phone 363-6576

Additional personnel:

|  | Doug Anderson (IOS) Melanie Quenneville (IOS) Lizette Beauchemin (IOS) Cindy Wright (IOS) Peter You (visiting scientist, IOS) Petteri Saarinen (IOS) |
| --- | --- |

Ship’s equipment required:

GPS positioning

Depth sounder

Loran C

Radar

Deck machinery required:

CTD/Rosette winch

Small side winch

Other equipment to be loaded:

Laboratory instruments and computers

CTD/rosette

Freezers

Provisional schedule:

Monday, April 26: Load the equipment at IOS.

Monday, April 26: When loading is completed and equipment tested, sail to the mouth of  Juan de Fuca Strait and start CTD stations. A first test station will be done in Saanich inlet near the Met buoy.

Tuesday - Sunday (April 27-May 2): proceed with the list of stations. Because we sample nutrients, discharges from the ship should be on hold while on station.

Sunday, May 2: Complete the stations in the northern Strait of Georgia. As soon as completed, sail back to Pat Bay and unload material.

Station list:

CTD/R Stations:

| Sta | Lat | Lat_mn | Lon | Lon_mn | Depth | ### Activity |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 49 | 20.30 | 124 | 12.10 | 247 | CTD |
| 2 | 49 | 24.10 | 124 | 9.30 | 289 | CTD Ox |
| 3 | 49 | 26.60 | 124 | 20.20 | 327 | CTD Ox |
| 4 | 49 | 24.50 | 124 | 22.10 | 344 | CTD |
| 5 | 49 | 27.40 | 124 | 30.80 | 315 | CTD |
| 6 | 49 | 30.60 | 124 | 27.80 | 192 | CTD Ox |
| 7 | 49 | 34.40 | 124 | 24.20 | 357 | CTD |
| 8 | 49 | 39.30 | 124 | 33.00 | 355 | CTD |
| 9 | 49 | 35.50 | 124 | 38.30 | 170 | CTD Ox |
| 10 | 49 | 40.70 | 124 | 47.30 | 95 | CTD |
| 11 | 49 | 42.40 | 124 | 43.40 | 289 | CTD |
| 12 | 49 | 43.60 | 124 | 40.80 | 357 | CTD Ox |
| 13 | 49 | 55.30 | 124 | 55.20 | 219 | CTD |
| 14 | 49 | 53.00 | 124 | 59.60 | 311 | CTD Ox |
| 15 | 49 | 51.60 | 125 | 1.60 | 143 | CTD |
| 16 | 49 | 57.70 | 125 | 8.80 | 146 | CTD Ox |
| 17 | 49 | 58.80 | 125 | 4.30 | 265 | CTD |
| 18 | 49 | 59.20 | 124 | 58.90 | 146 | CTD |
| 19 | 50 | 1.20 | 124 | 52.90 | 283 | CTD |
| 20 | 49 | 47.20 | 124 | 32.30 | 311 | CTD |
| 23 | 50 | 15.0 | 125 | 23.0 | 240 | CTD Ox |
| 22 | 49 | 40.20 | 124 | 16.30 | 358 | CTD |
| 21 | 50 | 2.0 | 125 | 13.6 | 72 | CTD |
| 24 | 49 | 30.30 | 124 | 6.00 | 430 | CTD |
| 25 | 49 | 27.70 | 124 | 7.50 | 320 | CTD |
| 26 | 49 | 14.30 | 123 | 50.80 | 256 | CTD |
| 27 | 49 | 19.10 | 123 | 48.00 | 347 | CTD Ox |
| 28 | 49 | 24.10 | 123 | 45.30 | 134 | CTD |
| 37 | 49 | 13.60 | 123 | 20.70 | 219 | CTD |
| 38 | 49 | 12.00 | 123 | 26.40 | 296 | CTD |
| 39 | 49 | 9.80 | 123 | 33.00 | 388 | CTD Ox |
| 40 | 49 | 8.60 | 123 | 36.80 | 146 | CTD |
| 41 | 49 | 3.30 | 123 | 22.30 | 247 | CTD |
| 42 | 49 | 1.80 | 123 | 26.20 | 326 | CTD Ox |
| 43 | 49 | 0.20 | 123 | 30.10 | 187 | CTD |
| 44 | 48 | 56.80 | 123 | 6.00 | 119 | CTD |
| 45 | 48 | 53.90 | 123 | 8.40 | 128 | CTD |
| 46 | 48 | 51.40 | 123 | 10.80 | 179 | CTD Ox |
| 47 | 48 | 49.30 | 123 | 6.20 | 188 | CTD |
| 48 | 48 | 51.70 | 123 | 3.20 | 220 | CTD |
| 49 | 48 | 55.00 | 122 | 59.60 | 132 | CTD |
| 50 | 48 | 57.70 | 122 | 56.10 | 26 | CTD |
| 51 | 48 | 46.70 | 122 | 51.60 | 155 | CTD |
| 52 | 48 | 38.90 | 122 | 43.30 | 91 | CTD |
| 53 | 48 | 33.20 | 122 | 45.00 | 73 | CTD |
| 54 | 48 | 26.60 | 122 | 44.30 | 77 | CTD |
| 56 | 48 | 46.40 | 123 | 1.60 | 214 | CTD Ox |
| 57 | 48 | 44.00 | 123 | 8.10 | 141 | CTD |
| 58 | 48 | 43.00 | 123 | 14.30 | 338 | CTD |
| 59 | 48 | 37.80 | 123 | 14.60 | 227 | CTD Ox |
| 60 | 48 | 33.90 | 123 | 12.80 | 298 | CTD |
| 61 | 48 | 29.20 | 123 | 9.20 | 274 | CTD |
| 62 | 48 | 22.80 | 123 | 2.60 | 150 | CTD Ox |
| 63 | 48 | 14.60 | 122 | 58.50 | 154 | CTD |
| 64 | 48 | 12.80 | 123 | 5.80 | 97 | CTD |
| 65 | 48 | 15.90 | 123 | 9.80 | 121 | CTD Ox |
| 66 | 48 | 19.30 | 123 | 14.10 | 104 | CTD |
| 67 | 48 | 22.80 | 123 | 18.10 | 106 | CTD |
| 68 | 48 | 12.20 | 123 | 43.00 | 137 | CTD |
| 69 | 48 | 15.60 | 123 | 43.20 | 174 | CTD Ox |
| 70 | 48 | 19.20 | 123 | 43.20 | 154 | CTD |
| 71 | 48 | 22.20 | 123 | 59.40 | 115 | CTD |
| 72 | 48 | 18.60 | 124 | 4.00 | 192 | CTD Ox |
| 73 | 48 | 15.00 | 124 | 6.70 | 157 | CTD |
| 74 | 48 | 25.10 | 124 | 35.60 | 192 | CTD |
| 75 | 48 | 28.20 | 124 | 32.80 | 230 | CTD Ox |
| 76 | 48 | 31.40 | 124 | 30.00 | 93 | CTD |
| 101 | 48 | 25.40 | 124 | 45.14 | 143 | CTD |
| 102 | 48 | 30.00 | 124 | 44.00 | 260 | CTD Ox |
| 103 | 48 | 33.00 | 124 | 43.00 | 125 | CTD |
| 104 | 48 | 20.00 | 123 | 18.00 | 70 | CTD |
| 105 | 48 | 11.00 | 123 | 19.00 | 80 | CTD |
| ADC | 48 | 14.00 | 123 | 18.00 | 113 | CTD Ox |
| SG2 | 49 | 1.43 | 123 | 23.97 | 270 | CTD |
| GVRD1 | 49 | 35.52 | 124 | 38.28 | 169 | Grab sample |
| GVRD7 | 49 | 3.34 | 123 | 22.16 | 233 | Grab sample |
| GVRD2 | 49 | 19.3 | 123 | 18.4 | 76 | Grab sample |