Work Schedule for Thursday, 8 June 2006

- 0000hrs to 0800hrs track GPS drifters deployed near Gormely Pt.

- 0800 Recover all GPS drifters

- Recover light trap deployed at Wicklow Pt. using small boat

- CTD/rosette sampling (see following Table 1 for list of stations and sampling order)

- Deploy light traps at Fox Island  site (50° 43.05’N, 126° 35.89’W) and Cypress Harbour (50° 50.23’N, 126° 39.96’W) using small boat.

- Plankton tows close to shore in Wells Passage and Sutlej Channel using small boat.

Watches:

0000-0400:  Lucius & Scott (drifters & CTD/rosette sampling)

0400-0800:  Dario (Drifter tracking)

0800-1200:  Hugh (Drifter recovery and light traps)

1200-1600:  Moira (Plankton tows)

1200-1600:  Lucius & Scott  (CTD/rosette sampling)

1600-2000:  Dario & Dave (CTD/rosette sampling)

2000-2400:  Hugh & Moira (Light traps & CTD/rosette sampling)

Table 1.  Bond Sound, Tribune Channel, Kingcome Inlet and Fife Sound.

| Station | Lat (N) | Long. (W) | Depth (m) | # of Samples |
| --- | --- | --- | --- | --- |
| RaP (1) | 50° 46.53’ | 126° 30.56’ | 220 | 11 |
| PP1 | 50° 48.8’ | 126° 31.5’ | 140 |  |
| Kin0 (2) | 50° 51.70’ | 126° 37.20’ | 400 | 2 |
| SC (1) | 50° 53.4’ | 126° 45.7’ | 230 | 11 |
| WP0.5 | 50° 52.86’ | 126° 53.23’ | 163 |  |
| WP (1) | 50° 50.85’ | 126° 56.4’ | 180 | 10 |
| QCS2 | 50° 46.6’ | 127° 02.3’ | 220 |  |
| QCS1.5 (1) | 50° 42.87’ | 126° 55.6’ | 145 | 9 |
| QCS1 | 50° 40.0’ | 126° 46.3’ | 150 |  |
| RP1 (1) | 50° 40.36’ | 126° 39.73’ | 70 | 6 |
| RP3 | 50° 43.44’ | 126° 34.73’ | 60 |  |

1.  DO Sampling Depths:
0, 10, 20, 30, 50, 75, 100, 125, 150, 175, 200, 250, 300, 400, 500, 600 or bottom -5m.

2.  Salinity sample for calibration of CTD at depth of 300m or greater