INSTITUTE OF OCEAN SCIENCES  CRUISE PLAN

SCIENCE CRUISE NUMBER:	2006-20 (8 to 13 may 2006)

NAME OF SHIP/PLATFORM:  	GRIZZLY COAST

PROJECT

Pilot study to develop methodologies for sampling the distribution of planktonic sea lice larvae in the Broughton Archipelago

SURVEY AREA/AREA OF OPERATION:
Broughton Archipelago, Tribune Channel and surrounding areas.

CRUISE OBJECTIVE[S]:

- Plankton tows for determination of distribution of planktonic larvae of sea lice in and around the Burdwood finfish farm and at non farm locations (Tribune Channel and Broughton Archipelago)

- Deploy SFU light traps from floating structures where possible.

- CTD profiles at plankton sampling locations and at mid-channel stations when time is available.( Tribune Channel and Broughton Archipelago)

DATE:		FROM:	8 May 2006			TO:  13 May 2006

SCIENTIFIC PERSONNEL:

Hugh Maclean – Senior Tech. (IOS – 250 363-6594

Moira Galbraith (IOS 250-363-6692)
Christina ??  (SFU student)

SHIP EQUIPMENT REQUIRED:

Depth sounder
DGPS for accurate positioning of stations

Use of small boat for plankton tows close to shore and in shallow waters.

DECK MACHINERY REQUIRED:

Davit with hydraulic winch to be used for plankton net tows and CTD casts

Submersible pump for washing down plankton nets

Sampling trays for washing and processing plankton samples

OTHER EQUIPMENT TO BE LOADED:

SFU Light traps c/w batteries, electronics and mooring components

Microscope for plankton sample analyses

Self-contained CTD (Seabird SBE25)

Two plankton nets
Niskin water sampling bottles with messenger

Salinity sample bottles and containers for preservation of plankton samples

Lap top computers

DANGEROUS CHEMICALS:

GAS CYLINDERS: 	NONE

ACIDS: 	NONE

BASES:	NONE

TOXIC: 	Formalin

FLAMMABLES: 	Ethanol (2litres)

RADIOISOTOPES:	NONE

ANTICIPATED LOADING TIME:

Afternoon of Monday May 8th in Port McNeill.

PROPOSED CRUISE ITINERARY:

| Date | General Area of Operations |
| --- | --- |
| 8 May | - Drive from IOS to Port McNeill with DFO vehicle - Load sampling equipment onto Grizzly Coast - afternoon departure for Burdwood Farm - before docking at accommodation float at Burdwood farm (Mainstream) contact manager of Burdwood farm and request information on biosecurity procedures - unload personal gear, food stuffs and sampling equipment at accommodations float - deploy light traps in Burdwood Islands - plankton tows and CTD sampling at stations near farm site (Fig. 1) and around the Burdwood Islands |
| 9 May | - recover light traps in the AM - plankton net tows at predetermined locations or at coordinated sampling locations with Marty or Brent - deploy light traps at the end of the work day - time permitting mid-channel CTD stations (Appendix A) |
| 10 May- | - recover light traps in the AM - plankton net tows at predetermined locations or at coordinated sampling locations with Marty or Brent - deploy light traps at the end of the work day - time permitting mid-channel CTD stations (Appendix A) |
| 11 May | - recover light traps in the AM - plankton net tows at predetermined locations or at coordinated sampling locations with Marty or Brent - deploy light traps at the end of the work day - time permitting mid-channel CTD stations (Appendix A) |
| 12 May | - recover light traps in the AM - plankton net tows at predetermined locations or at coordinated sampling locations with Marty or Brent - deploy light traps at the end of the work day - time permitting mid-channel CTD stations (Appendix A) |
| 13 May | - recover light traps in the AM - CTD profiles along route to Port McNeill - Depart Port McNeill for IOS with DFO vehicle |

Figure 1.  Burdwood Farm

APPENDIX A (if there is time for additional CTD profiles do the following stations)

Mid-Channel CTD Sampling Lines

Line 1.  Knight Inlet to Kingcome Inlet .

| Station | Lat (N) | Long. (W) | Depth (m) |
| --- | --- | --- | --- |
| Kn2 | 50° 39.3’ | 126° 11.0’ | 165 |
| TrC0.5 | 50° 40.8’ | 126° 14.60’ | 145 |
| TrC1S | 50° 43.6’ | 126° 10.9’ | 300 |
| TS1 | 50° 47.21 | 126° 02.23 | 160 |
| TrC1.5 | 50° 45.60’ | 126° 09.05’ | 221 |
| TrC2 | 50° 49.21’ | 126° 12.76’ | 200 |
| BoS1 | 50° 51.81 | 126° 10.82 | 121 |
| TrC2.5S | 50° 50.41’ | 126° 19.75’ | 300 |
| TrC3 | 50° 48.96’ | 126° 25.38’ | 238 |
| PP1 | 50° 48.8’ | 126° 31.5’ | 140 |
| Kin0S | 50° 51.70’ | 126° 37.20’ | 400 |

Line 3.  Tribune Channel to Fife Sound to Queen Charlotte Strait to Knight Inlet (40nm).

| Station | Lat (N) | Long. (W) | Depth (m) |
| --- | --- | --- | --- |
| TrC3 | 50° 48.96’ | 126° 25.38’ | 238 |
| PP1 | 50° 48.8’ | 126° 31.5’ | 140 |
| FiSS | 50° 47.0’ | 126° 36.7’ | 325 |
| QCS1 | 50° 40.0’ | 126° 46.3’ | 150 |
| BlS | 50° 36.0’ | 126° 43.65’ | 130 |
| Kn0 | 50° 38.28' | 126° 34.98' | 55 |
| Kn1 S | 50° 38.1' | 126° 25.3' | 247 |

Line 4.  Penphrase Pass. to Sutlej Channel to Wells Passage (20nm).

| Station | Lat (N) | Long. (W) | Depth (m) |
| --- | --- | --- | --- |
| PP1 | 50° 48.8’ | 126° 31.5’ | 140 |
| Kin0S | 50° 51.70’ | 126° 37.20’ | 400 |
| SC | 50° 53.4’ | 126° 45.7’ | 230 |
| WP | 50° 50.85’ | 126° 56.4’ | 180 |

Line 5.  Penphrase Passage to head of Kingcome Inlet (long run to head of Kingcome Inlet) (30nm).

| Station | Lat (N) | Long. (W) | Depth (m) |
| --- | --- | --- | --- |
| PP1 | 50° 48.8’ | 126° 31.5’ | 140 |
| Kin0S | 50° 51.70’ | 126° 37.20’ | 400 |
| Kin1S | 50° 53.6' | 126° 34.5' | 476 |
| Kin1.5S | 50° 56.2' | 126° 28.9' | 477 |
| WS1 | 51° 01.06’ | 126° 31.4’ | 200 |
| Kin2 S | 50° 55.5' | 126° 23.2' | 375 |
| Kin3 | 50° 54.9' | 126° 14.7' | 216 |

Line 6.  CTD stations inside sill of Knight Inlet sill (34nm).

| Station | Lat (N) | Long. (W) | Depth (m) |
| --- | --- | --- | --- |
| Kn4 S | 50° 40.9' | 125° 56.2 | 439 |
| Kn5 | 50° 41.6' | 125° 47.0' | 366 |
| Kn6 S | 50° 45.3' | 125° 41.1' | 512 |
| Kn7 | 50° 48.1' | 125° 37.3' | 523 |
| Kn8 S | 50° 52.3' | 125° 38.7' | 512 |
| Kn9 | 50° 54.3' | 125° 32.8' | 401 |
| Kn10 S | 50° 58.6' | 125° 33.5' | 366 |
| Kn11 | 51° 02.5' | 125° 34.0' | 203 |

Line 7. Outer Knight Inlet and Clio Channel (31nm).

| Station | Lat (N) |  | Long. (W) |  | Depth (m) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Kn2 | 50° 39.3' |  | 126° 11.0' |  | 165 |  |  |
| CC1 | 50° 36.3' |  | 126° 21.4' |  | 108 |  |  |
| CC2 | 50° 34.2' |  | 126° 29.3' |  | 65 |  |  |
| Kn1S | 50° 38.1' |  | 126° 25.3' |  | 247 |  |  |
| Kn0 | 50° 38.28' |  | 126° 34.98' |  | 55 |  |  |
| QCS4S |  | 50° 46.65’ |  | 127° 24.28’ |  | 405 |  |
| QCS5 |  | 50° 49.43’ |  | 127° 12.04’ |  | 140 |  |
| QCS6 |  | 50° 52.41’ |  | 127° 21.61’ |  | 145 |  |

S , Salinity sample for calibration of CTD at depth.

Current meter mooring locations (for information purposes only)

| KiW-02 | 50° 39.38’ | 126° 09.87’ | 180 |
| --- | --- | --- | --- |
| TCS-02 | 50° 43.18’ | 126° 12.03’ | 200 |