Progress report on Dr. C.S. Wong’s data archival

September 19, 2009

Joe Linguanti

Final Status Report February 14, 2014 (see the Status and Next Steps section)

Robin asked for a progress report on moving Dr. Wong’s data to the OSD archive specifically;

- pCO2 data – Sophie

- Alkalinity – Lisa and Jim

- Sediment traps – Robie

- Everything – John Page

A request went out to the four contacts listed above for a short summary on the status of the datasets associated with their names. Their responses are included below in the Summaries section. Status and next steps follow.

SUMMARIES

Comments in Bold and Italics are mine.

- pCO2 Data – Sophie

Here is what we have accomplished so far with the pCO2 data and the measurement programme.

Archived data

-All the paper chart records have been digitized and entered into Excel spreadsheets in a common format. (URAS-II analyzer 1973-1986).

-All of the electronic pCO2 and auxiliary data for 1973-2003  (temperature, salinity, atmospheric pressure, wind speed, metadata and comments) have also been converted to a common electronic format.

-Linearity of the system response has been checked for every cruise.

-Data collected after 2003 were not included in the rescue project, but I have since evaluated the 2004-2005 data that John Page has processed and the first cruise from 2009.  The 2006-2008 data have not been processed yet, but John Page is beginning to work on them.  The useable data up to 2005 will be included in the data report and paper.

-Sources of error are noted in the data files.

-A data report, “Canadian Data Report of Fisheries and Aquatic Sciences #1201” is in preparation.  It still needs one summary figure that Jim Christian is going to prepare and a final edit.

Measurement programme

-Many problems were identified with the data collection programme.  These had resulted from a lack of scientific oversight of the programme.

-With only a little encouragement, Mike Arychuk and Marty Davelaar have since corrected all the problems with the procedure and the instrument and have overseen the rewriting of the LabView software.  They have implemented a log book and a daily checklist and identified and corrected the cause of the excessive noise in the data.  They, with Keith Johnson, have collected good data on two cruises this year (January and June line P cruises).  These data have been partly processed for archiving.  We will streamline the processing and archival for the next cruise. Spohie has agreed that as part of the streamlined process the data will be send to me.

Next steps

-Complete data report.  Expected completion August 31, 2009.

-Reformat data sheets for archiving.  Now that I have tried to use the data to write a paper, it is clear that the original format that we chose for archiving is rather clumsy and inefficient.  Also, now that I am aware of the international standard format for pCO2 data recommended by CDIAC (Carbon Data Information and Analysis Center) and SOCAT (Surface Ocean Carbon Atlas), I would like to store our data in the same format.

-Conduct primary quality control (or maybe this is secondary): bad data identified at the time of collection or during the data rescue effort have already been flagged, but now that I have a better idea of what level of primary QC is expected by the international community, I would like to go through each sheet myself.  Expected completion October 31, 2009 (maybe sooner, but I don't want to have to apologize later for missing the deadline.) At that point the data will go into the IOS archive in their final form.  They are currently on the osdcommon drive, but I wouldn't recommend that anyone use them yet.

-Once the primary QC is completed, I will go through and delete all the bad data before submitting the data set to CDIAC and SOCAT.

- Alkalinity Data

Lisa

I've actually not been dealing with the historical data, but leaving that to Jim, while i focus on making sure things are up to snuff now. Between Jim and Keith, you should be able to get the information about the current status that you're looking for. That said, my understanding is that Jim has gotten almost if not all of the historical alkalinity and TIC data from the North Pacific into CDIAC and that it's currently being quality controlled as part of an international, pan-Pacific effort. Coastal and Arctic data may be a different matter, though.

Jim

That is correct. I have only the Line P data. I have assigned quality flags to all data (a prerequisite for contributing data to the international synthesis). Some values may change (adjustments that are a 'best guess' to correct discrepancies among different data sets that are likely to be analytical rather than real).

We can (1) put these data in the IOS data archive as they are, (2) wait until the adjustments are made, or (3) archive both original and adjusted values.

- Sediment Trap Data – Robie

The sediment trap time series at Station P has been archived as Excel spreadsheets.  David Timothy, under contract, has gone through the entire set and weeded out inconsistencies within the tables and between tables and paper trail.  It turned out to be a bit more tedious than planned, but it is now done.  The data are now in common format and the archive contains the minimum required reporting - that is, we have not made columns of derived parameters but these could be made using the various reported analytical and field data.   Along the way, David has looked at replicates, for which there are several categories.  We've also done some stepwise PCA and the like on the data to look for irregularities.  It's now as good as we can make it.

- Everything – John Page

I'm not sure how much detail you want with this.

Here is the short version:

pCO2 Data (NE Pacific)

- Currently working on data set from LineP Cruises (1973 - 2009) for pCO2 paper by CS Wong, Sophie, Emmy, Jim Christian, ...

- Of the above I am now working on raw pCO2 data for 2006 cruises (2006-08, 2006-13, 2006-15).

- Data from 2007, 2008 cruises is expected to be junk, due to incorrect use of Scrubber filter on pCO2 system.

- Awaiting for thermosal data for 2009 cruise before it can be prepared for processing.

- None of the pCO2 data from LineP has been sent to the OSD archive.

- Waiting until the data set is complete (pressure to complete for the paper in progress) and for opinion of the authors on any problem data.

- Quite a bit of QC done on the data (and auxiliary data) so that bad data was rejected & suspect data flagged.

- Final data to archive should be just uncorrected XCO2 and (computed) pCO2.

- The Met data and T,S data were (usually) heavily interpolated to match frequency of XCO2 measurements, so should not be archived in same file as XCO2 & pCO2.

LineP Bottle Data

- I have sent you data for 1956 to 1969 cruises, which you have added to the OSD Archive. Progress report in OSDCommon/John Pages Archive/John Pages Arhive.doc.

- I have sent you data for 1970 cruises - but you did not have time to add due to your work on other projects.

- On hold 1971 - 200x.  Will resume sending stuff when you are ready.

- I have done quite a bit of QC on the cast data, but mixed layer data is quite variable and harder to QC.

- Some additional work may be required eventually after addition to OSD archive by someone else.

- I was looking for Alkalinity, DIC data for 2006-2008 LineP Cruises in the OSD Archive last week, and did not find any.

- I assume that Marty has given the values to Lisa Miller and she is sitting on them for some reason?? Lisa has send me most of the data but I have not has an opportunity to archive it yet.

Ship of Opportunity Data

- Lots of surface measurements from a variety of platforms (Skaugran, MV Lillooet, Canada Maru, Canadian Ace, ...) including Nutrients, Alkalinity, DIC, SST, Sal, ...

- Basic QC has been done of the above (typo corrections to Date,Time, Lat,Lng after plotting cruise tracks, computing ships speed, ... also pCO2 for MV Lillooet (but was missing Met data for computing pCO2 from XCO2).

- None of this stuff has been sent for inclusion in the OSD data archive.

Moored Sediment Trap Data

- Did lots of work helping David Timothy do the final archive data set preparation, initially starting with my data set then adding % composition from Excel files of Janet Barwell-Clarke.  I think he is finished assembling the data but I don't know if he has finished the paper for publication, or forwarded the data for archival.

- David has made a huge effort to do very careful QC on the final data set.

Free Drifting Sediment Trap Data

No one has ever looked at this data yet.  David Timothy was hoping to get a contract to do that. Robie mentioned that he would like to contract David to do this work.

Basically the barriers in doing this is the time required to do each bit.  Once the pCO2 data is off my plate, I can concentrate on just archiving whatever I have.

So that will require someone on the receiving end to put the data in the OSD archive.  Meanwhile I can be getting data into a format suitable for archiving.

I am hoping that the LineP pCO2 data will be complete this fall.

STATUS AND NEXT STEPS

Final status for each of the datasets is provided after Next Steps. Complete processing notes can be found in document Consolidation of John Page's Archive 2006.doc.

pCO2

Status

- 1973 – 2005 data has been gathered into several spreadsheet files.

- Primary quality control (QC) completed. Expected that secondary QC will be completed by October 31, 2009.

- 2006 data in early stages of processing by John Page.

- 2007, 2008 data is questionable.

Next Steps

- Get John to complete 2006 data by ASAP and pass to Sophie for QC. Aim to be completed by November 30, 2009.

- Ascertain quality of 2007, 2008 data.

- Convert 1973 – 2006 data into IOS Header Format (IHF) and place into Ocean Science Data Archive (OSDA).

- Conversion should be relatively easy as these files are self contained time series files that do not need to be merged with other data sets.

Completed January 14, 2014

The data from 1973 to 2009 were quality controlled by Sophie and put into the OSDA. The data from 2007 to 2008 was not salvageable so it did not get processed.

Alkalinity and TIC

Status

- Data has been gathered.

- Primary QC completed. No timeline for when secondary QC will be completed.

- Data in CDIAC format.

Next Steps

- Write an IOS Header converter for CDIAC format (would be useful for Sophie’s data as well.)

- Recommend that data be placed into IOS archive as they are since Jim feels that secondary QC could be a long time coming and that any changes would probably be few.

- These data would require more time to place into the OSDA since they would need to be merged with their corresponding bottle files. I would suggest that they be done at the same time as John’s bottle data are being consolidated into the archive.

Completed February 12, 2012.

- The primary quality controlled DIC and Alkalinity data from 1986-2001 were merged with their corresponding bottle profiles in the OSDA. The data from 1985 was not archived since it was deemed to be of poor quality (pre coulometric method).

- The CDIAC format is just a spreadsheet file so there was no requirement to write a conversion routine. Tools from IOS Shell were used instead.

Sediment Traps

Status

- Data has been gathered into several spreadsheets.

- QC completed.

- Robie would like to have a year while paper is being published before data is place is OSDA.

Next Steps

- Determine appropriate format for archiving the data and prepare conversion routine.

- Place data into OSDA in a year’s time.

Completed February 2014.

Both the moored (1989-2006) and free floating (1987-2005) sediment trap files were sent to me by David Timothy.  The Excel files were converted to IOS Header format and put into the OSDA.

Bottle Data

Status

- Primarily nitrates from profiles and loop data.

- 1956-1970 data have been added to the corresponding cruises in the OSDA.

Next Steps

- Continue adding to the OSDA

- Processing of this dataset is a bit more involved as it requires a lot of cross referencing with different Physics and Chemistry cruise and cast numbers (in the earlier year).

- There should not be many additions in the profile data in the latter years, 1991 onward, since around this time much of the data was centrally managed.

Completed January 10, 2011.

For each of the years 1959 to 1988 John produced an Excel file containing both the sea surface and profile data that were not in the OSDA.  The files for each year were converted to the IOS Header format and added to the OSDA. The data for the years after 1988 were acquired from other sources who worked with CS Wong (see section on Additional Data Sets below).

Ships of Opportunity

Status

- Data in John Page’s archive with basic QC completed.

Next Steps

- Add to the OSDA

- Should be relatively easy as just a simple conversion is required.

Updated Status

This dataset has many unresolved issue that John did not have time to complete. Many of the times recorded were not in UTC but instead local time was used making standardizing the time series difficult. Different sampling techniques between oceanographic technicians and crew make QC difficult. Analysis of Total Alkalinity and DIC samples is still backlogged. The care done by the ship’s crew is poor so the quality of much of the data is questionable. All these issues will require significant effort to get the data ready for the OSDA. It will require somebody with an interest in the dataset to put in the require effort.

Additional Data Sets

Additional dataset were added to the OSDA from people that worked for CS Wong.

- Productivity Data. Completed February 20, 2012

Starting in 1989 the productivity profiles which included Primary Productivity, Chlorophyll, Nutrients, POC and PON were acquired from Frank Whitney’s productivity Excel files. Prior to 1989 John Page had included these data in his annual spreadsheet files. The last year added from Frank’s files was 2004.  Each of the productivity profiles were converted to IOS Header and copied to the OSDA.

- Chlorofluorocarbon (CFC) Data. Completed June 28, 2013.

The CFC data provided by Wendy Richardson spanned the years 1992 to 1999. For each cruise the spreadsheet file and document describing methods were copied to the Cruise .DOC directory in the OSDA.

- Iron Data. Completed June 11, 2013.

Excel spreadsheet files containing iron data from 1997 to 2011 were received from Keith Johnson. Nes Sutherland had compiled the data into the spreadsheet files. Each of the iron profiles were converted to IOS Header and copied to the OSDA.

- Dimethyl Sulphide Data (DMS). Completed October 28, 2013.

DMS files provided by Wendy Richardson and Mike Arychuk spanned the years 1996 to 2005. Each of the DMS profiles were converted to IOS Header format and merged with their corresponding profiles in the OSDA.

BARRIERS

Now the most of the datasets are ready for insertion into the OSDA, the primary barrier is the lack of knowledgeable resources to convert the files to IHF and place them in the archive. This task was mine until I took the assignment with Savi. A couple of years ago I taught Peter Chandler how to put files into the archive  which were already in the proper format as part of the regular processing stream such as the CTD and bottle files. I never got around to walking Peter through the process of converting files, validating channels names and metadata, merging were necessary with existing files, etc, since both Peter and I simply lacked the time.

In November I hope to use any time available from my present assignment, augmented by some OT (we discussed this earlier) to start moving these datasets into the archive. At the same time I should have someone working with me so that we can have more then one person with this capability.

The question is who? I suspect that Peter has his eye on some opportunities that may become available soon due to staff departures. John Page is retiring soon. I don’t feel that Andrew, Kerry and Edmand are suitable for this task. I would propose that if possible we create a new PC-02 position (or we could back fill Peter’s position if he were to advance) and pick a good young candidate from the pool being created now. This person would be hired with the intent of providing Data Management services for the division well into the future.